Elm Street Community Arts Center

Weekend Workshop Expansion — Planning Notes

Status: APPROVED by Program Committee — June 30, 2026

Prepared by: Program Coordinator  |  Distribution: Program Committee, Executive Director

# Background and Goal

Weekend workshop attendance has been flat for three consecutive quarters. The Spring 2026 member survey (42 respondents, collected May 1–June 28) shows steady interest in pottery and painting, a preference for Saturday sessions, and cost and childcare as the two most common barriers to attending. This document evaluates three ways to expand the weekend workshop schedule for Fall 2026 and recommends criteria for choosing between them.

Goal: increase weekend workshop attendance by 20% over the Fall 2026 quarter, without exceeding the approved program budget.

# Budget and Constraints

Approved program budget: $4,500 for the quarter (instructor stipends, supplies, and marketing combined)

Room availability: Studio A is open Saturday and Sunday, 9:00 a.m.–4:00 p.m. only

Staffing: Two staff members are certified to supervise weekend sessions; no weekend overtime budget remains

Marketing lead time: Flyers and newsletter placement require 3 weeks' notice before a session launches

Childcare: No on-site childcare currently offered; a part-time sitter would cost $20/hour

# Options Under Consideration

All three options fit within the approved budget individually. Only one option will be funded for the Fall 2026 launch.

|  | Option A: Saturday Pottery | Option B: Sunday Photography Walk | Option C: Friday Evening Painting Social |
| --- | --- | --- | --- |
| Day / time | Saturday, 10:00–12:00 | Sunday, 1:00–3:00 | Friday, 6:00–8:00 |
| Format | 6-week series, beginner wheel-throwing | Drop-in, single session, outdoors + gallery critique | Drop-in, single session, guided social painting |
| Target audience | Adults and teens 14+ | All ages, families welcome | Adults 21+ |
| Instructor cost | $60/session x 6 = $360 | $45/session | $50/session |
| Supply cost | $18/participant (clay, glaze) | $0 (participants use own devices) | $12/participant (paint, canvas) |
| Capacity | 12 participants | 20 participants | 16 participants |
| Childcare offered | No | Not needed (family format) | No |
| Estimated cost to launch | $576 (6 weeks, 12 participants, incl. supplies) | $45 (1 session) | $242 (1 session, 16 participants) |

# Success Metrics

Attendance: fill at least 75% of session capacity by the second offering

Retention: at least 30% of attendees return for a second weekend session within the quarter

Cost per attendee: stay at or below $30 per attendee once launch costs are included

Survey follow-up: post-session rating of 4.0 or higher (5-point scale)

# Decision Needed

The Program Committee has approved moving forward with exactly one option for the Fall 2026 launch. The Program Coordinator will compare the three options above against the survey findings and this quarter's budget, and bring a one-page recommendation with a comparison table to the next committee meeting.

# Approval

| Approved by | Program Committee (unanimous vote, June 30, 2026) |
| --- | --- |
| Executive Director sign-off | Approved June 30, 2026 |
| Next review | End of Fall 2026 quarter, alongside attendance and budget results |