Project planning meeting notes

Customer self-service portal pilot

| Date | July 30, 2026 |
| --- | --- |
| Time | 10:00-10:35 a.m. |
| Attendees | Priya Shah, Jordan Miles, Nina Walker, and Leo Chen (vendor) |
| Not attending | Maya Patel, regional manager |

## Progress update

42 of 50 employee accounts are active.

18 of 20 help articles are published. Priya said the remaining two are drafted.

Twelve employees joined the first test. Ten completed every task without help.

## Discussion

Password-reset emails sometimes take up to 15 minutes to arrive. Leo said the vendor's email queue settings may be causing the delay, but the cause is not confirmed.

The group agreed to keep the August 14 launch target for now. The password-reset process must be fixed and retested by August 4 for that date to remain realistic.

The team will ask Maya to approve up to US$750 for extra vendor troubleshooting by August 1.

The final launch decision meeting will take place on August 7.

## Actions recorded

Leo: Investigate the email queue and report findings by August 3. Status: In progress.

Priya: Publish the remaining two help articles by August 5. Status: Not started.

Nina: Retest password reset on August 4, after the vendor fix. Status: Waiting.

Jordan: Train the support team by August 6. Status: Scheduled.

Prepare the recommendation for the August 7 launch decision meeting. Owner and status were not recorded.

## Risk noted

If password-reset emails are still delayed after August 4, the August 14 launch may need to move.