WEEKLY OPERATIONS BRIEFING

Strong demand creates one decision for next week

Week ending July 31, 2026

Audience: Managing Director and Program Manager

Prepared: July 31, 2026

Status: Draft for human approval

In brief: Four workshops were delivered to 58 attendees. Overall attendance was 80.6%, known net revenue was £11,340, and average satisfaction was 4.5 out of 5 from three reported sessions.

# What changed this week

Present with Confidence had the highest attendance rate, with 17 of 18 places filled. Its satisfaction survey remains open.

Project Planning had the lowest attendance rate, with 9 of 16 places filled. The approved sources do not explain the lower result.

Next week's AI for Office Tasks session is full, and four people are on the waitlist.

# Decision and actions

| Item | Owner | Due | Status |
| --- | --- | --- | --- |
| Approve or decline an August 14 AI for Office Tasks overflow session. | Managing Director | Aug. 3, noon | Decision needed |
| Confirm Leo Martin as backup instructor for August 4. | Program Manager | Aug. 1 | In progress |
| Send Harbor & Finch an estimate for a private September session. | Sales Lead | Aug. 5 | Not started |

# Risks and missing information

Backup instructor confirmation for August 4 is still pending.

Satisfaction covers three of four delivered sessions. The remaining survey closes August 3.

No approved revenue forecast is available for the proposed overflow session.

# Supporting evidence

Weekly-Workshop-Tracker.xlsx, Weekly Results rows 6-9 and Summary cells B4-B8.

Weekly-Workshop-Tracker.xlsx, Next Week row 9.

Team-Update-Notes.docx, Next-week schedule; Client and sales follow-up; Decisions and actions.

Previous-Weekly-Briefing.docx was used for structure only.