APPROVED SOURCE

Team Update Notes

Week ending July 31, 2026

Compiled by: Maya Chen, Program Manager

Updated: July 31, 2026 at 12:00 PM

Status: Approved for the weekly operations briefing

# Program delivery

The Present with Confidence survey remains open until August 3. Do not treat its satisfaction score as zero.

Two attendees from Introduction to Data Visualization asked about an advanced follow-up course. No date has been agreed.

The Project Planning session produced one corporate training inquiry. The sales team has not yet confirmed scope or value.

# Next-week schedule

The August 6 AI for Office Tasks session is full. Four people are on the waitlist.

Recommendation: add an overflow AI for Office Tasks session on August 14, subject to the managing director's approval by noon on August 3.

Leo Martin is the proposed backup instructor for the August 4 Introduction to Data Visualization session. Confirmation is due by August 1.

# Client and sales follow-up

Harbor & Finch requested an estimate for a private 12-person Project Planning session in September.

Owner: Dana Brooks, Sales Lead. Send the estimate by August 5.

Do not include the client's contact details in the briefing.

# Decisions and actions

| Item | Owner | Due | Status |
| --- | --- | --- | --- |
| Approve or decline the August 14 overflow session | Managing Director | Aug. 3, noon | Decision needed |
| Confirm backup instructor for August 4 | Program Manager | Aug. 1 | In progress |
| Send Harbor & Finch estimate | Sales Lead | Aug. 5 | Not started |

# Known limits

The reason for Project Planning's lower attendance is not known.

No revenue forecast has been approved for the proposed overflow session.

Satisfaction data is complete for three of the four delivered sessions.