# Weekly Project Update

Customer Self-Service Portal Pilot

To: Maya Patel, Regional Manager

From: [VERIFY]

Date: July 30, 2026

# Status at a Glance

Overall status: Amber. The planned August 14 launch remains possible if the email problem is fixed by August 4.

# Approval Needed

Please approve up to US$750 for additional vendor troubleshooting by August 1.

# What's Causing the Delay

Password-reset emails sometimes take up to 15 minutes to arrive. The vendor believes its email queue settings may be causing the delay and is investigating.

# Progress So Far

- 42 of 50 employee accounts have been activated.

- 18 of 20 help articles have been published.

- Twelve employees took part in the first test.

- Ten testers completed every task without help.

# Next Steps and Timeline

- Fix and retest the password-reset process.

- Publish the remaining two help articles.

- Train the support team.

- Hold the final launch decision meeting on August 7.