Proposal: Standardized Monthly Client Reporting

Prepared for Ridgeline Bookkeeping  •  Prepared by Dana Ruiz, Independent Consultant  •  3 August 2026

| ① | OUTCOME Consistent, error-free monthly client reports delivered on the same schedule every month, cutting your team's preparation time and reducing client questions about inconsistent formatting. |
| --- | --- |
| ② | SCOPE Included: - A working session to audit your current reporting process and templates. - A standardized report template covering the five metrics your clients see most often. - A Claude-assisted drafting workflow your team can run each month, with a written how-to guide. - One round of revisions after the first live report cycle. Not included: bookkeeping data entry or corrections to underlying financial records. |
| ③ | PRICE $1,800 flat fee, covering everything listed under Scope. Two rounds of revisions to the template are included after the first live cycle. Work outside this scope, such as templates for additional report types, will be quoted separately. |
| ④ | TIMELINE - Week 1: Discovery session and audit of your current process. - Week 2: Draft the template and the workflow guide. - Week 3: Live test run on one client report, with adjustments based on your feedback. - Week 4: Handoff and a walkthrough with your team. |

This proposal is valid for 14 days. Questions about scope or timing are welcome before we begin.